# Minutes

Bicycle Board Education Committee

Meeting date: 30 September 2010; 8:30 – 9:30 am

Meeting location: Zen Clay

Meeting objectives: Define a plan that can be implemented immediately to get outcome metrics: indicators of bicyclist and motorist behavior changes as a result of the education program.

Participants: Chip Wamsley, Ryan Post, gunnar Shogren, Paul Becker, Jim Rye, Don Spencer, Frank Gmeindl (scribe)

Action Items: (Grey font signifies action items that were closed during the meeting.)

| Due date | Responsibility | Action Item |
| --- | --- | --- |
| TBD | Wamsley | 62. Determine deadline for Mountaineer Yellow Pages ad submission. |
| TBD | Shogren | 63. Lead design of Yellow Page ad |
| TBD | Gmeindl | 64. Send MEBEP Executive Summary to Jim Rye |
| TBD | Gmeindl | 65. Get follow-up evaluation instruments that other LCIs use |
| TBD | Becker | 66. Finalize logic model and give to Jim Rye |
| TBD | Rye | 67. Present executive summary, proposal and logic model to Reagan Curtis to get Program Evaluation thrust to measure MEBEP outcomes. |
| TBD | Becker | 68. Determine if Journalism (Communication) would measure MEBEP outcomes. |
| TBD | Gmeindl | 69. Arrange follow-up meeting with Paula Fitzgerald to get Marketing students to measure MEBEP outcomes. |

Added from 10/6 BB meeting

| 10/7/2010 | Spencer | 70. (formerly BB #110) Contact the former head of the WVU Communications Dept. to see if he can assist with the radio PSAs. |
| --- | --- | --- |
| 10/7/2010 | Spencer | 71. (formerly BB #112) Contact area Boy Scout troops to see if there is interest in a revised version of Confident City Cycling that kids can take. He will refer interested parties to Frank. |

Discussion/Conclusions:

- We discussed output vs. outcome measures.

- Since we have diffuse impact, we’ll need a powerful measurement tool.

- Developing and implementing a MEBEP outcomes measurement program could be a Master or PhD thesis project.

- Consider using the Retrospective Pre-test Methodology after a participant has completed a CCC class to determine participant attitudes before and after the class.

- For future participants, get their knowledge, attitudes and behaviors (KAB) before they take the class and then after.

- Re-use measurement instrument shown successful by other LCIs.

- Personal testimony can be as powerful as objective data if the testimony is valid.

- Consider a well designed follow up survey for past CCC graduates that could also produce useful personal testimony documents.

- Consider an area of the BikeMorgantown web site “for motorists”.

- Consider using the new Share the Road.  It’s the Law! bumper sticker as an incentive or reward for providing information, e.g. MEBEP outcome measurement.

Agenda for Next Meeting

TBD