Morgantown Municipal Bicycle Board

Meeting Minutes

date: December 12, 2008

location: Morgantown Public Safety Building

objective: Develop Bicycle Parking Recommendations

Participants: Chip Wamsley, Jonathan Rosenbaum, Don Spencer Frank Gmeindl (recorder)

Action Items

| Due date | Responsibility | Action Item |
| --- | --- | --- |
| 11/25/2008 | Gmeindl | 62. Obtain a schematic of the layout of the downtown parking garage for possible rack placement. |
| TBD | Hein | 63. Complete Sketch Up of racks on High St. |
| 12/05/2008 | Gmeindl | 64. Ask Jeff Mikorski to buy a flare rack. |

Action Item Status

#62 - Open.  Tom Arnold promised to provide Frank drawings.

#63 – Open.  Nick will complete sketchup of racks on High St.

#64 – Open. Frank will ask Jeff Mikorski to buy 1 flare style rack so we can test it and use it to get a perspective of the locations at which we plan to put them.

New Business

- We reviewed a method for weighting the rack selection criteria and the applying the criteria to the selection options but decided we needed to identify all the options before we could prioritize them.

- We looked through catalogs and drew various designs on the white board including flare, inverted U, loop-and-post, Pittsburgh’s “P” design and penny-farthing cycle design and estimated prices for each.

- We argued about the relative importance of the criteria that the whole Bicycle Board identified when it identified bike racks and bike parking as the highest priority obstacle to achieving our vision and concluded that everyone in the City must have a positive reaction to whatever bike racks we select.

- We discussed sponsoring a design contest.

- We discussed modifying off-the-shelf designs, particularly of the inverted U rack, to provide a distinctive Morgantown design.

- We discussed putting bike corrals that would occupy one car parking space, be protected by bollards and have inverted U racks located in three locations: 1) in front of the Blue Moose, 2) inside the Black Bear parking garage, 3) at the corner of High and Fayette in front of Subway.

- We discussed asking Tom Arnold, Parking Authority Director, to identify parking spaces for bicycle corrals after we explain considerations for cyclists proximity to popular destinations and safety.

Next Meeting

We didn’t plan the next meeting.

Meeting Evaluation

We didn’t evaluate the meeting.  Sure could have used more members though.