Morgantown Municipal Bicycle Board

Regular Meeting Minutes

August 5, 2010

Public Safety Building

Open Action Items:

| Due date | Responsibility | Action Item |
| --- | --- | --- |
| TBD | Springston | 71. Collect information from cities that have already implemented the SLM. |
| 09/02/10 | Gmeindl | 90. Contact absent members of the BB and ask them what it would take to get them to participate. |
| Closed | Gmeindl | 104. Find out who to contact at the CVB regarding printing of the Bike Map. Closed at August 5, 2010 meeting. |
| 09/02/10 | Hein | 107. Prepare a detailed proposal of the Youth Bicycle Education plan, including an outline of class design and the detailed actions that the BB will be expected to take. |
| 09/02/10 | Rye | 108. Talk to Bob Roberts re: in-line grates on Evansdale Dr. |
| 09/02/10 | Rosenbaum | 109. Try to find document on MUTCD summary of bicycle-related signage. |
| 09/02/10 | Spencer | 110. Contact the former head of the WVU Communications Dept. to see if he can assist with the radio PSAs. |
| 08/02/10 | Spencer | 111. Find out what is going on with his assigned article, entitled “Bikes and Pedestrians.” |
| 09/02/10 | Spencer | 112. Contact area Boy Scout troops to see if there is interest in a revised version of Confident City Cycling that kids can take. He will refer interested parties to Frank. |
| Closed | Burkhart | 113. Design bumper stickers for BikeMorgantown.com. Closed at August 5, 2010 meeting. |
| 09/02/10 | g. Shogren | 114. gunnar to initiate contact with U92 radio personality. |
| 09/02/10 | Burkhart | 115. Coordinate with gunnar on the development of a Yellow Page community page. |
| 09/02/10 | Burkhart | 116. Contact Sign Factory about production and cost of the bumper sticker. |
| 09/02/10 | Rosenbaum | 117. Contact Public Theatre actors about radio ads. |
| 09/02/10 | Gmeindl | 118. Prepare draft of brainstorming activities for MPO Conference. |

Meeting Minutes:

Agenda Item 1 (Schmooze time)

The August 2010 monthly meeting of the Morgantown Municipal Bicycle Board (BB) was called to order at 6:30 p.m. at the Public Safety Building by Chairman Frank Gmeindl with the following members attending:

- Frank Gmeindl, Aira Burkhart, Don Spencer, Hugh Kierig, Marilyn Newcome, Jonathan Rosenbaum, and Chip Wamsley.

- Absent members: Jonathan Zerbe, Chet Parsons, Alice Vernon, Derek Springston, Jim Rye, Paul Becker, Betsy Shogren, gunnar Shogren, and Don Dickerson.

- Visitors: None

Agenda Item 2 (Secretary)

Hugh agreed to record the minutes in Betsy Shogren’s absence.

Agenda Item 3 (Agenda)

The agenda was approved without change.

Agenda Item 4 (Minutes of Last Meeting)

The minutes from the July meeting were approved without change.

Agenda Item 5 (Action Items)

- #71 – Open.  Springston was absent.

- #90 – Open.

- #104 – Closed. Frank met with Jeff Huffman.

- #107 – Open. Hein was absent.

- #108 – Open.

- #109 – Open.

- #110 – Open. Spencer was absent at this time.

- #111 – Open. Spencer was absent at this time.

- #112 – Open. Spencer was absent at this time.

- #113 – Closed.  Burkhart presented bumper sticker.

Agenda Item 6 (Ripe Banana Issues) - None

Agenda Item 7 (Education Status)

Frank reported that:

- The video spots are complete and the plan is to run them on cable

- Billboard photos are being shot.

- No radio PSA’s yet.

- Jonathan will talk with the Public Theatre actors about working on the radio.

Agenda Item 7.a (Review of Bumper Sticker)

Aira presented the art and copy for the new bumper sticker for Bikemorgantown.org.  It was approved by the Board.  Aira will contact Sign Factory about production and costs.

Agenda Item 8 (Bicycle Parking)

The Morgantown bicycle parking rings have been delivered with the installation expected to be complete by mid-August.

Agenda Item 9 (MPO Conference)

The Bicycle Board has been asked to participate in three events for the October Statewide Conference of MPO Officials that is sponsored by the Morgantown MPO.  These events are:

- A 30-minute presentation at the conference to educate the officials of the needs of bicyclists.  The presentation will be made jointly with Bicycle Boards from Charleston and Parkersburg.  It was suggested that the content of the Morgantown presentation mirror that of a presentation Frank made to the MPO in January of 2009.  Also focus on the mark-up of shared lanes, accomplishments of the education grant, and topo constraints in implementing climbing lanes.

- A mobile lab throughout Morgantown designed to educate the MPO and Transportation officials on needs, issues, and ideas that can be shown.  This lab will be conducted jointly with the Pedestrian Safety Board.  Specifically want to highlight on the lab the benefits of traffic markings, Mountaineer Station, and the rail-trail system.

- Development of a display table that promotes biking and hazards that bicyclists deal with.

Thanks to Marilyn for capturing the following points made during the brainstorming session for ideas to include in the presentation, bus ride and display table:

- January MPO presentation given by Frank: Widen lanes; shared lane markings

- Example of Shared Lane marking; Bicycles May Use Full Lane signage

- Bus Ride:

  - Place markings on Universiy Ave.

  - Have cyclists on the road to demonstrate how cars can get around bike on wide lane but not on typical narrow road

  - Photoshop shared lane markings on photos of the bus route and hand out to participants on the bus so they can visualize difference they would make for cyclists

  - “Chalk” some temporary shared lane markings on the road

  - Take bus on typical routes that cyclists currently take e.g. University, Overhill, Jones

  - Bad intersections: Road – rail trail crossings

  - Multi-modal stations (Mountaineer Station)

- Accomplishments of Education Grant

- Climbing Lanes and where needed (hills)

- Show multi-modal at University on bus ride

- Maps of Shared Lane Markings (Dererk’s map)

- Pictures of cyclist in-line grate accident

- History of cycling: why we need to increase cycling.  List reasons: obesity, etc.

- Establish a training area for bicycling before getting on the road

Agenda Item 10 (Mon Blvd Bike Lane)

Don indicated that liability issues prohibit volunteer work for the construction.  Material for installation will be approximately $11,000.  Budget constraints at the City prohibit the construction now but by Spring 2011 there may be funding available.  This issue is currently dead.

Agenda Item 11 (Finances)

Frank distributed a packet detailing the Effective Bicycling Education Program Financial summary for July 2010.  All present members of the BB approved the finances.

Agenda Item 12 (New Action Items)

#114. gunnar to initiate contact with U92 radio personality.

#115. Aira to coordinate with gunnar on the development of a Yellow Page community page.

#116. Aira to contact Sign Factory about production and cost of the bumper sticker.

#117. Jonathan to contact the WV Public Theater about actors to do radio ads.

#118. Frank will prepare draft of brainstorming of the content for the MPO conference presentations.

Agenda Item 14 (Meeting Evaluation)

+	No comments.

Chairman Gmeindl adjourned the meeting at ~8:30 pm.  The next meeting is planned for September 2, 2010 at 6:30 PM.

Minutes respectfully submitted this date by Betsy Shogren, 08/25/10.

Attendance:

|  | Feb-09 | Mar-09 | Apr-09 | May-09 | Jun-09 | Jul-09 | Aug-09 | Sep-09 | Oct-09 | Nov-09 | Dec-09 |  | Jan-10 |  | Feb-10 |  | Mar-10 |  | Apr-10 |  | May-10 |  | Jun-10 |  | Jul-10 |  | Aug - 5 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Becker, Paul | X | X |  |  |  |  |  |  |  |  |  |  | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Burkhart, Aira |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | X |  | X |  |  |  | X |  | X |  | X |
| Dickerson, Don | X | X |  | X |  |  |  |  |  | X |  |  |  |  | X |  | X |  |  |  |  |  |  |  |  |  |  |
| Gmeindl, Frank | X | X | X | X | X |  | X | X |  | X | X |  | X |  | X |  | X |  | X |  | X |  | X |  | X |  | X |
| Kierig, Hugh |  | X |  | X | X |  |  | X |  | X | X |  |  |  | X |  | X |  |  |  |  |  | X |  |  |  | X |
| Newcome, Marilyn |  | X | X | X | X |  | X | X |  |  | X |  |  |  | X |  | X |  | X |  | X |  | X |  |  |  | X |
| Parsons, Chet |  |  |  | X |  |  |  |  |  | X | X |  |  |  |  |  | X |  | X |  |  |  |  |  |  |  |  |
| Rosenbaum, Jonathan | X | X | X | X | X |  | X | X |  | X | X |  |  |  |  |  |  |  |  |  | X |  | X |  | X |  | X |
| Rye, Jim | X | X | X | X | X |  |  | X |  |  |  |  | X |  | X |  | X |  |  |  | X |  | X |  | X |  |  |
| Shogren, Betsy |  |  | X | X | X |  | X |  |  | X | X |  | X |  | X |  | X |  | X |  | X |  | X |  | X |  |  |
| Shogren, gunnar |  | X | X | X | X |  | X |  |  | X | X |  | X |  |  |  |  |  | X |  | X |  | X |  | X |  |  |
| Spencer, Don | X | X | X |  |  |  |  | X |  | X |  |  | X |  | X |  | X |  | X |  | X |  | X |  | X |  | X |
| Springston, Derek |  | X |  | X | X |  | X |  |  | X | X |  |  |  | X |  |  |  | X |  |  |  | X |  |  |  |  |
| Vernon, Alice |  | X | X | X |  |  | X |  |  |  | X |  | X |  |  |  | X |  |  |  |  |  | X |  |  |  |  |
| Wamsley, Chip | X | X | X | X | X |  | X | X |  | X | X |  |  |  |  |  | X |  | X |  | X |  | X |  |  |  | X |
| Zerbe, Jonathan |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | X |  |  |  |  |  |  |
| X=Present |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Blank = Absent |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |