Charleston Land Trust

Action Plan and Goals - 2011

Goal No. 1:  Establish Reputation that Charleston is Healthiest City in USA

| Projects | Action to be Taken | Responsible Party | Goals | Status |
| --- | --- | --- | --- | --- |
| Establish Biking, Hiking, Running Trail System | - Establish Trails - Street Markings - Rating System - Ordinance - Teams - Timeline - Contest - Bike Racks - Amenities See separate Definitive Plan | Ned Rose Dennis Strawn | Establish 100 miles of Biking, Jogging and Hiking Trails |  |
| Publicity/ Public Relations | Consolidate web pages (Neighborwoods; CLT and City) Develop brochures, maps, enhance websites Produce information brochures and organize campaigns to highlight the best of Charleston’s offerings: Hikes; bike trails; jogging trails; golf; swimming; art; history; music; fun More cooperation between City, CVB and others Promote Safety, particularly with SHARE THE ROAD signs “Best of Charleston/ Kanawha Valley ...” -- walking/ biking trails Focus on Riverfront/ Haddad Develop name for the Riverfront which captures the fact that it is a park, and perhaps the most used of any | Mary Stanley | New Year’s resolution: Healthiest City Publish weekly walking/biking/running trails |  |
| Lawson Hamilton Property | Secure funding for acquisition and acquire | Bill Mills | Acquire by June 2011 Clean up, repair sanitary sewer (Sanitary Board), provide for erosion control Incorporate into city park and trail system, linking MacCorkle with Danner Meadow Park |  |
| Chilton Property | Easements for adjoining property Volunteers for clean up and maintenance | Lewis Payne | Clear invasive vines and other undesirable vegetation Create walking, hiking trail Secure easements Eagle Scout Project |  |
| Wallace-Hartman Property | Support “Friends of Wallace Hartman” | Lewis Payne |  |  |
| Barton Street Property |  | Pat McGill West Side Main Street |  |  |
| Carriage Trail/ Justice Row Property | Support beautification efforts | Mary Stanley | Traffic control at Justice Row |  |
| Beautification of Riverfront South (along river from Frontier to Trojan Landing) | Develop plan for removing unwanted vegetation and selectively trimming and removing trees. | Troy Stallard |  |  |
| Activities/ Athletic Events | Series of athletic events focused on specific Land Trust properties to promote interest and support for the Land Trust |  |  |  |
| Oil & Gas Development/ Blackwell | Securing Blackwell oil and gas development agreement and using money for CLT projects |  |  |  |
| Participate in City’s Comprehensive Plan |  | Mary Jean Davis Dan Vriendt |  |  |
| Acquire New Property for Public Use (west side) |  |  |  |  |
| Capitol Market Greenspace |  |  |  |  |
| Sculptured Flower Garden (Jeff Fetty) Hole in south side bridge |  | Tom Lane |  |  |
| Establish name for Kanawha Boulevard Park |  | Ned Rose |  |  |

3337101.1