# Minutes

Bicycle Board Education Committee

Meeting date: 3 August 2010, 8-9 am

Meeting location: Blue Moose Cafe

Meeting objectives:

1. Select networks to broadcast spots.

2. Leader and plan to get videos broadcast.

3. Leader and plan to complete billboards.

4. Leader and plan for free ad in Mountaineer Yellow Pages.

Participants: Chip Wamsley, Ryan Post, gunnar Shogren, Frank Gmeindl (scribe)

Action Items: (Grey font signifies action items that were closed during the meeting.)

| Due date | Responsibility | Action Item |
| --- | --- | --- |
| TBD | Wamsley | 56. Negotiate with Comcast to get spots broadcast within budget. |
| 8/15/2010 | Wamsley/Gmeindl | 57. Present Comcast proposal to Mikorski |
| TBD | Shogren/Post | 58. Create final billboard graphic image. |
| TBD | Gmeindl | 59. Work with Rodosta to complete billboard designs |
| TBD | Wamsley | 60. Arrange billboard deal with Lamar. |
| 8/15/2010 | Wamsley/Gmeindl | 61. Present Lamar proposal to Mikorski |
| TBD | Wamsley | 62. Determine deadline for Mountaineer Yellow Pages ad submission. |
| TBD | Shogren | 63. Lead design of Yellow Page ad |

Discussion/Conclusions:

- We selected the following networks on which the video spots will be aired: Discovery, TBS, CNN, Comedy Central, CMT and Travel Channel.

- Chip will negotiate with Comcast to get the package within the budget.

- Tentatively the spots will be aired mid-August to mid-October but this may be modified to fit the budget.

- Once an acceptable deal is defined, Cbip and Frank will present it to Jeff Mikorski who will engage Comcast.

- Thanks to gunnar, Ryan, Betsy and JR Petsko for shooting many photos as candidates for the billboard graphic.

- We selected and cropped a best photo but gunnar and Ryan with discuss with JR the possibility of doing another shoot to obtain an even better photo.

- Frank will take the final selected photo to Gary Rodosta to define the billboards.

- Chip will arrange with Lamar a proposal to display the billboards.

- Frank and Chip will present the Lamar proposal to Jeff Mikorski who will engage Lamar.

- Shawn Mason of Mountaineer Yellow Pages has offered us a whole page in the Mountaineer Yellow Pages.

- Chip will ask Shawn when the page content must be submitted.

- Gunnar will lead the page content definition.

Agenda for Next Meeting

TBD